## Sprint plan
Market POS sprint plan
Taoliyuan ¦ Individual project ¦ Deadline 24 November 2026 ¦ Estimates are story points
Sprint | Start | End | Goal | Planned points | Open points
1 | 2026-10-15 | 2026-10-17 | Cash sale and stock | 16 | 0
2 | 2026-10-18 | 2026-10-20 | Returns and history | 15 | 0
3 | 2026-10-21 | 2026-10-23 | Documentation and delivery | 8 | 3
Ideal daily burndown below is a plan. Actual completion evidence is on Actual checkpoints.
Sprint 1 day | Ideal points | Actual daily points
0 | 16 | 16
1 | 10.6667
2 | 5.3333
3 | 0
Sprint 2 day | Ideal points | Actual daily points
0 | 15 | 15
1 | 10
2 | 5
3 | 0
Sprint 3 day | Ideal points | Actual daily points
0 | 8 | 8
1 | 5.3333
2 | 2.6667
3 | 0
Daily actual cells are intentionally blank after the baseline. Do not infer daily progress from same-day checkpoints. Update them only after observing the corresponding day. Planned sprint dates remain timeboxes even when implementation completes early.

## Backlog
Product backlog and acceptance criteria
Source: supplied Software Engineering Practice Assignment; implementation and verification on 15 October 2026.
ID | Epic | User story | Priority | Points | Sprint | Status | Acceptance criteria | Evidence
US01 | Sale | As a cashier, I want to find products and edit quantities so that I can build an accurate basket. | Must | 3 | 1 | Done | Two milk units and one bread show EUR 8.20. | Browser checkout screenshot
US02 | Sale | As a cashier, I want to accept cash and calculate change so that I can complete a sale. | Must | 5 | 1 | Done | EUR 10.00 tendered for EUR 8.20 yields EUR 1.80 change. Insufficient cash fails. | Cash sale and rollback tests
US03 | Sale | As a cashier, I want a stored receipt so that I can identify a completed sale. | Must | 3 | 1 | Done | Receipt contains a unique ID, original prices, quantities, total and payment. | Receipt and restart tests
US04 | Inventory | As a store operator, I want stock updated atomically so that quantities stay consistent. | Must | 5 | 1 | Done | Sales reduce stock. Rejected and concurrent excess sales cannot overdraw stock. | Atomicity and concurrency tests
US05 | Return | As a cashier, I want to retrieve a receipt so that I can check return eligibility. | Must | 3 | 2 | Done | Lookup shows purchased, already returned and remaining quantities. | Return lookup and missing receipt tests
US06 | Return | As a cashier, I want partial cash refunds so that customers can return selected items. | Must | 5 | 2 | Done | One milk unit refunds EUR 2.50 using the original price and restores one unit. | Partial return and original price tests
US07 | Return | As a store operator, I want excess and repeated refunds prevented so that cash is protected. | Must | 5 | 2 | Done | Retries have one effect. Cumulative returns never exceed quantities sold. | Idempotency and concurrent return tests
US08 | History | As a store operator, I want transaction history so that I can reconcile net sales. | Should | 2 | 2 | Done | EUR 8.20 sales less EUR 2.50 refunds gives EUR 5.70 net. | Browser history and net total test
US09 | Documentation | As an assessor, I want analysis, design and verification evidence so that I can trace the solution. | Must | 5 | 3 | Done | Both use cases, UML models, report, workbook and presentation are readable and consistent. | Report, UML, workbook and 12-slide presentation reviewed
US10 | Delivery | As an assessor, I want the source repository and demonstration video so that I can inspect and run the project. | Must | 3 | 3 | Open | Both branches are available remotely and a published English presentation video is linked. | Requires repository push, student recording and upload
Total points |  |  | 39 | Remaining points |  |  |  | 3
Completed points |  |  | 36 | Completion |  |  |  | 92.31%

## Actual checkpoints
Observed implementation checkpoints
Actual timestamps use Asia/Shanghai. These are evidence checkpoints, not simulated daily sprint results. Points burn only after verification. Publication and student recording remain open.
Observed time | Checkpoint | Remaining points | Commit | Evidence
2026-10-15 22:02 | Plan baseline | 39 | f2811d3 | Acceptance criteria established; no verified story completion
2026-10-15 22:02 | Implementation | 39 | b44e312 | Features implemented; acceptance not yet verified
2026-10-15 22:08 | Verification | 8 | 314bd47 | US01-US08 verified with 22 tests and browser walkthrough